## updated APP
4th Updated Annual Procurement Plan FY 2015
PROCUREMENT PROGRAM / PROJECT | END-USER | Mode of Procurement | [12 empty] | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (Brief Description of P/P)
|  |  | Pre-Procurement Conference | Ads/ Post of IAEB | Pre-bid Conference | Eligibility Check | Submission and Opening of Bids | Bid Evaluation | Post Qualification | NOA | Contract Signing | NTP | Delivery Completion | Acceptance / Turnover |  | Total | MOOE | CO
AUDIO VISUAL EQUIPMENT | HEATH PROMOTION AND COMMUNICATION SERVICE (HPCS)-BLOOMBERG | NEGOTIATED PROCUREMENT AGENCY TO AGENCY (PS-DBM) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | FAPS | 49000
| OFFICE OF ASEC BAYUGO | NEGOTIATED PROCUREMENT AGENCY TO AGENCY (PS-DBM) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | FAPS | 8000
|  | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | FAPS | 120000
SUB-TOTAL | [15 empty] | 177000
COMPUTER EQUIPMENT / HARDWARE / SOFTWARE | OFFICE OF ASEC BAYUGO | NEGOTIATED PROCUREMENT AGENCY TO AGENCY (PS-DBM) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | FAPS | 108860.96
|  | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | FAPS | 380000
| OFFICE OF THE SECRETARY (OSEC) | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 20000
| BUREAU OF INTERNATIONAL HEALTH COOPERATION (BIHC)-PGMU | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | FAPS | 800000
| KNOWLEDGE MANAGEMENT AND INFORMATION TECHNOLOGY SYSTEM (KMITS) | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 5406392
SUB-TOTAL | [15 empty] | 6715252.96
CONTRACT OF SERVICE | ADMINISTRATIVE SERVICE (AS) | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 46043813.6
| CENTER FOR DEVICES AND REGULATION RADIATION HEALTH AND RESEARCH (CDRHHR) | NEGOTIATED PROCUREMENT (TWO FAILED BIDDINGS) | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | FAPS | 12000000
| HEALTH EMERGENCY MANAGEMENT BUREAU (HEMB) | DIRECT CONTRACTING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 29480
| HPCS | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 1500000
| KMITS |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 71052000
| PHARMACEUTICAL DIVISION (PD) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 31374136.72
| PHILIPPINE NATIONAL AIDS COUNCIL (PNAC) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 10640
SUB-TOTAL | [15 empty] | 162010070.32
CONSULTANCY SERVICES | DISEASE PREVENTION AND CONTROL BUREAU-OCCUPATIONAL DISEASES DIVISION (DCPB-ODD) | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 2800000
| DPCB-ESSENTIAL NON-COMMUNICABLE DISEASE DIVISION (DCPB-ENCDD) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 2000000
| DPCB-LIFESTYLE RELATED DISEASES DIVISION (DCPB-LRDD) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 10000000
| DPCB-ENVIRONMENTAL RELATED HEALTH OFFICE (DCPB-ERDD) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 3800000
| DPCB-INFECTIOUS DISEASE FOR PREVENTION AND CONTROL DIVISION (IDPCD) -FILARIASIS AND SCHISTOSOMIASIS PROGRAM |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 6000000
| HEALTH HUMAN RESOURCE DEVELOPMEN TBUREAU (HHRDB) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 2000000
| HPCS |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 9164400
| KMITS |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 26500000
| PNAC |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 500000
| QUALITY MANAGEMENT SYSTEM OFFICE (QMSO) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 7500000
SUB-TOTAL | [15 empty] | 70264400
DRUGS AND MEDICINES | DPCB-IDPCD (MALARIA PROGRAM) | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 4997783.1
| DCPB-ERDD |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 13735041.1
| DPCB - WOMENS MEN'S AND CHILDREN HEALTH DIVISION (DCPB-WMCHDD) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 771591956.76
| DPCB-IDPCD (LEPROSY PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 6405574
| DPCB-IDPCD (EMEREGING AND RE-EMERGING PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 18499960.05
| DPCB-IDPCD (FILARIASIS PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 117458000
| DPCB-IDPCD (HIV AIDS PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 182051443.6
| DPCB-IDPCD (INTEGRATED HELMINTHIASIS PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 15823080
DRUGS AND MEDICINES | DPCB-IDPCD (LEPROSY PROGRAM) | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 18798531
| DPCB-IDPCD (MALARIA PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 7240000
| DPCB-IDPCD (SCHISTOSOMIASIS PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 42592401.72
| DPCB-IDPCD (TB CONTROL PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 435717464.9
| HEMB | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 59252150
|  | NEGOTIATED PROCUREMENT AGENCY TO AGENCY (PITAHC) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 18954000
| OSEC | NEGOTIATED PROCUREMENT AGENCY TO AGENCY (PITAHC) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 4095000
SUB-TOTAL | [15 empty] | 1717212386.23
REHYDRATION SOLUTION | HEMB | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 81000
SUB-TOTAL | [15 empty] | 81000
VACCINES | DPCB-IDPCD (RABIES PROGRAM) | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 367759200
| DPCB - ENCDD | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 319549050
| DPCB-EPI PROGRAM | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 1766500000
|  | NEGOTIATED PROCUREMENT UN AGENCY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 490377500
SUB-TOTAL | [15 empty] | 2944185750
INSECTICIDE | IDPCB-IDPCD (MALARIA PROGRAM) | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 82459875
| DPCB-IDPCD (DENGUE PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 74386000
SUB-TOTAL | [15 empty] | 156845875
LABORATORY SUPPLIES AND REAGENTS | BIHC-TFM PROJECT | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | FAPS | 3515200
|  | REPEAT ORDER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | FAPS | 38002
|  | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | FAPS | 55999.44
| DPCB-IDPCD (HIV AIDS PROGRAM) | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 30797380
| DPCB-IDPCD (TB CONTROL PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 113040361
| DPCB-EPI PROGRAM |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 100000000
LABORATORY SUPPLIES AND REAGENTS | DPCB-WMCDD | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 15000000
| HEMB |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 6127500
| DPCB-IDPCD (SCHISTOSOMIASIS PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 900000
SUB-TOTAL | [15 empty] | 269474442.44
FAMILY PLANNING COMMODITIES | DCPB-WMCHDD | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 650429000
SUB-TOTAL | [15 empty] | 650429000
HEALTH DEVICE AND EQUIPMENT | CDRHHR | NEGOTIATED PROCUREMENT (TWO FAILED BIDDINGS) | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | FAPS | 4800000
|  | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 4911850
| DPCB-IDPCD (DENGUE PROGRAM) | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 25993600
| DPCB-IDPCD (EMEREGING AND RE-EMERGING PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 10000000
| DPCB-IDPCD (HIV AIDS PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 31100960
| DPCB-ENCDD |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 775000
| DPCB-EPI PROGRAM |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 60000000
| DCPB-WMHDD |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 6000000
| HEMB |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 3200000
| DPCB-IDPCD (MALARIA PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 2944000
SUB-TOTAL | [15 empty] | 149725410
EVENT ORGANIZER | BLHSD | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 4800000
| DCPB-ENCDD |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 2000000
| DPCB-IDPCD (HIV AIDS PROGRAM) |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 2000000
| DPCB-ENCDD |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 2000000
SUB-TOTAL | [15 empty] | 10800000
IEC MATERIALS | BIHC TFM PROJECT | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | FAPS | 1424000
| DCPB-ENCDD | NEGOTIATED PROCUREMENT AGENCY TO AGENCY (APO) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2013 | 3rd week June 2013 | 3rd week June 2013 |  |  | GOP | 6093300
| DCPB-WMHDD | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 7375000
| DPCB-IDPCD (RABIES PROGRAM) | NEGOTIATED PROCUREMENT AGENCY TO AGENCY (APO) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 10800000
IEC MATERIALS | DPCB-IDPCD (TB CONTROL PROGRAM) | NEGOTIATED PROCUREMENT AGENCY TO AGENCY (APO) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2013 | 3rd week June 2013 | 3rd week June 2013 |  |  | GOP | 6378371
| DPCB-IDPCD (FILARIASIS PROGRAM) | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 110000
| DCPB-ERDD | NEGOTIATED PROCUREMENT AGENCY TO AGENCY (APO) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 1480000
| HEMB | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 14000000
|  | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 26500
| HHRDB | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 532000
| KMITS | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 400000
| HPCS | NEGOTIATED PROCUREMENT AGENCY TO AGENCY (APO) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 10290000
| PD | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 2216000
SUB-TOTAL | [15 empty] | 61125171
MACHINE / SUPPLIES AND EQUIPMENT | AS | SMALL VALUE | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | FAPS | 123000
| HPCS-BLOOMBERG | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | FAPS | 58000
| OFFICE OF ASEC UBIAL | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 37084.8
SUB-TOTAL | [15 empty] | 218084.8
MEDIA PALCEMENT | HPCS | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 51000000
| PD |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 14000000
| DCPB-WMHDD |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 40015000
SUB-TOTAL | [15 empty] | 105015000
ONLINE SUBSCRIPTION | CDRHHR | DIRECT CONTRACTING | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 382500
| LEGAL SERVICE | SMALL VALUE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 50000
| PD | DIRECT CONTRACTING | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 3000000
| OSEC | SMALL VALUE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 85750
SUB-TOTAL | [15 empty] | 3518250
PRINTING MATERIALS | HPCS | DIRECT CONTRACTING | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 399902
SUB-TOTAL | [15 empty] | 399902
SOUVENIR AND PROMOTIONAL ITEM | BIHC-TFM PROJECT | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | FAPS | 1500000
| BLHSD | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2013 | 2nd week May 2013 | N/A | N/A | 3rd week June 2013 | 3rd week June 2013 |  |  | GOP | 360000
| HEMB | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 750000
| HPCS |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 400000
| PD |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 815000
| PNAC |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 200000
SUB-TOTAL | [15 empty] | 4025000
GENERAL MERCHANDISE | HEMB | COMPETITIVE BIDDING | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 1250000
| HPCS |  | 3rd week March 2015 | 1st week April 2015 | 3rd week April 2015 | 1st week May 2015 | 1st week May 2015 | 2nd week May 2015 | 3rd week May 2015 | 1st week June 2015 | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 600000
SUB-TOTAL | [15 empty] | 1850000
VEHICLE SUPPLIES | BIHC-PGMU | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 110000
SUB-TOTAL | [15 empty] | 110000
ICE LINED REFRIGERATOR | HFDB | SHOPPING | N/A | N/A | N/A | N/A | 1st week May 2015 | 2nd week May 2015 | N/A | N/A | 3rd week June 2015 | 3rd week June 2015 |  |  | GOP | 489955000
TOTAL | [15 empty] | 489955000
OVERALL TOTAL | [15 empty] | 6804136994.75
3RD SUPPLEMENTAL
COMPUTER EQUIPMENT / HARDWARE / SOFTWARE | KMITS | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 13210000
SUB-TOTAL | [15 empty] | 13210000
CONSULTANCY SERVICES | PD | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 7000000
| KMITS |  | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 102518900
| HHRDB |  | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 13000000
| HPCS |  | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 4700000
| DPCB-WMCDD |  | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 6700000
SUB-TOTAL | [15 empty] | 133918900
CONTRACT OF SERVICE | HEMB | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 900000
| HHRDB | SHOPPING | N/A | N/A | N/A | N/A | 1st week August 2015 | 2nd week August 2015 | N/A | N/A | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 34920
| HFDB / HFEP | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 11000000
| LMD |  | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 10000000
| AS |  | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 32894114.4
SUB-TOTAL | [15 empty] | 21934920
DRUGS AND MEDICINES | PD | NEGOTIATED PROCUREMENT AGENCY TO AGENCY (APO) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 829281520.73
SUB-TOTAL | [15 empty] | 829281520.73
VACCINE | DPCB-ENCDD | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  |  | 41005000
| DPCB-EPI PROGRAM | [14 empty] | 449999960
SUB-TOTAL | [15 empty] | 491004960
FAMILY PLANNING COMMODITIES | DPCB-WMCDD | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 217125000
SUB-TOTAL | [15 empty] | 217125000
HEALTH DEVICE AND EQUIPMENT | DPCB-ENCDD | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 12418500
| DPCB-WMCDD | [14 empty] | 337500000
SUB-TOTAL | [15 empty] | 349918500
LABORATORY SUPPLIES AND REAGENTS | DPCB-WMCDD | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 285000000
| NVBSP EMERGENCY | EMERGENCY PROCUREMENT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week July 2015 | 1st week July 2015 |  |  | GOP | 11333600
SUB-TOTAL | [15 empty] | 296333600
EVENT ORGANIZER | HPCS | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 7000000
SUB-TOTAL | [15 empty] | 7000000
IEC MATERIALS | DPCB-WMCDD | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 4600000
| HPDPB | SHOPPING | N/A | N/A | N/A | N/A | 1st week August 2015 | 2nd week August 2015 | N/A | N/A | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 94200
SUB-TOTAL | [15 empty] | 4694200
MEDIA PLACEMENT | DPCB-IDPCD (TB PROGRAM) | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 30000000
SUB-TOTAL | [15 empty] | 30000000
ICE LINED VACCINE REFRIGERATOR | HFDB | NEGOTIATED PROCUREMENT UN AGENCY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 108243648
SUB-TOTAL | [15 empty] | 108243648
GENERAL MERCHANDISE | HEMB | SHOPPING | N/A | N/A | N/A | N/A | 1st week August 2015 | 2nd week August 2015 | N/A | N/A | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 605644
| HEMB |  | N/A | N/A | N/A | N/A | 1st week August 2015 | 2nd week August 2015 | N/A | N/A | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 348000
| HPCS |  | N/A | N/A | N/A | N/A | 1st week August 2015 | 2nd week August 2015 | N/A | N/A | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 475000
SUB-TOTAL | [15 empty] | 1428644
INFRASTRUCTURE | HFDB | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 4800000000
SUB-TOTAL | [15 empty] | 4800000000
VEHICLE | HFDB | COMPETITIVE BIDDING | 3rd week June 2015 | 1st week July 2015 | 3rd week July 2015 | 1st week August 2015 | 1st week August 2015 | 2nd week August 2015 | 3rd week August 2015 | 1st week September 2015 | 3rd week September 2015 | 3rd week September 2015 |  |  | GOP | 648000000
SUB-TOTAL | [15 empty] | 648000000
[15 empty] | TOTAL | 7952093892.73
4TH SUPPLEMENTAL
CONSTRUCTION SUPPLIES | AS | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 1371292
SUB-TOTAL | [15 empty] | 1371292
COMPUTER EQUIPMENT / HARDWARE / SOFTWARE | HHRDB | SHOPPING | N/A | N/A | N/A | N/A | 1st week November 2015 | 2nd week November 2015 | N/A | N/A | 3rd week December 2015 | 3rd week December 2015 |  |  | GOP | 31890
| KMITS | BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 13699999.2
| BIHC | SHOPPING | N/A | N/A | N/A | N/A | 1st week November 2015 | 2nd week November 2015 | N/A | N/A | 3rd week December 2015 | 3rd week December 2015 |  |  | FAPS (EU FUND) | 2489000
| PS | SHOPPING | N/A | N/A | N/A | N/A | 1st week November 2015 | 2nd week November 2015 | N/A | N/A | 3rd week December 2015 | 3rd week December 2015 |  |  | FAPS (EU FUND) | 275769.12
SUB-TOTAL | [15 empty] | 16496658.32
COMPUTER SUPPLIES | ENCDD-PHILNOS | SHOPPING | N/A | N/A | N/A | N/A | 1st week November 2015 | 2nd week November 2015 | N/A | N/A | 3rd week December 2015 | 3rd week December 2015 |  |  | GOP | 413000
| DPCB-IDO | REPEAT ORDER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3rd week November 2015 | 1st week December 2015 | 1st week December 2015 |  |  | GOP | 12598935
SUB-TOTAL | [15 empty] | 13011935
CONTRACT OF SERVICE | HHRDB | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 5500000
| BLHSD |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 43200000
SUB-TOTAL | [15 empty] | 48700000
CONSULTANCY SERVICES | KMITS | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 89418900
| DPCB/ EB/ KMITS | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 60876000
SUB-TOTAL | [15 empty] | 150294900
DRUGS AND MEDICINES | DPCB-IDPCD (MALARIA PROGRAM) | EMERGENCY PROCUREMENT | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 1st week December 2015 | 1st week December 2015 |  |  | GOP | 40875000
| DPCB-IDPCD (INTEGRATED HELMINTH PROGRAM) | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 15000000
| DPCB-FILARIASIS PROGRAM |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 15391427
| DPCB-IDO SCHISTOSOMIASIS |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 3541980
| DPCB-IDPCD (DENGUE PROGRAM) | REPEAT ORDER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 2172000
| DPCB-IDPCD (LEPROSY PROGRAM) |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 4112676.25
| HEMB |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 3541980
| DPCB-WMCHDD |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 51098029
| TB CONTROL PROGRAM |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 387000
SUB-TOTAL | [15 empty] | 133073912.25
FAMIL PLANNING COMMODITIES | WMCHDD (REPEAT ORDER) | REPEAT ORDER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3rd week November 2015 | 1st week December 2015 | 1st week December 2015 |  |  | GOP | 26572500
SUB-TOTAL | [15 empty] | 26572500
VACCINES | DPCB-IDPCD (RABIES PROGRAM) | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 22674988
| DPCB-IDPCD (RABIES PROGRAM) | REPEAT ORDER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 2474700
| DPCB-EPI PROGRAM | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 370290000
| DPCB-NATIONAL IMMUNIZATION PROGRAM |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 161793360
| DPCB-ENCDD |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 44200000
SUB-TOTAL | [15 empty] | 601433048
INSECTICIDE | DPCB-IDPCD (MALARIA PROGRAM) | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 20614875
SUB-TOTAL | [15 empty] | 20614875
HEALTH DEVICE AND EQUIPMENT | DPCB-IDPCD (DENGUE PROGRAM) | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 93500000
| DPCB-IDPCD (DENGUE PROGRAM) |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week November 2015 | 3rd week November 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | CONAP 2014 QRF | 131541700
| HFDB | NEGOTIATED PROCUREMENT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | CONAP 2014 | 3524094550
|  |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week November 2015 | 3rd week November 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 70000000
| CDRHHR | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week November 2015 | 3rd week November 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | FAPS (EU FUND) | 8900000
| FHO | NEGOTIATED PROCUREMENT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 52389369
SUB-TOTAL | [15 empty] | 3880425619
LABORATORY SUPPLIES AND REAGENTS | DPCB-IDPCD (TB CONTROL PROGRAM) | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 3164070
| DPCB-IDPCD (TB CONTROL PROGRAM) | REPEAT ORDER | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3rd week November 2015 | 1st week December 2015 | 1st week December 2015 |  |  | GOP | 1511894
| DPCB-IDPCD (MALARIA PROGRAM) | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 1808000
| DPCB-IDPCD (HIV PROGRAM) |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 4500000
SUB-TOTAL | [15 empty] | 10983964
IEC MATERIALS | KMITS | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 725000
| DPCB-IDPCD (LEPROSY PROGRAM) |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 5000000
| FMS | DIRECT CONTRACTING | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3rd week November 2015 | 1st week December 2015 | 1st week December 2015 |  |  | GOP | 96800
SUB-TOTAL | [15 empty] | 5821800
MEDIA PLACEMENT | DPCB-ELIMINATION DISEASE | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 38500000
SUB-TOTAL | [15 empty] | 38500000
INFRASTRUCTURE | HEMB | NEGOTIATED PROCUREMENT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | CONAP 2014 | 40000000
| HFDB | [8 empty] | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | FAPS (EU FUNDS) | 703000000
| HEMB | [8 empty] | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | FAPS (EU FUNDS) | 10000000
| OSEC | [8 empty] | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | FAPS (EU FUNDS) | 10935897
| BIHC | [8 empty] | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | FAPS (EU FUNDS) | 4000000
SUB-TOTAL | [15 empty] | 767935897
FURNITURE AND FIXTURE | AS | NEGOTIATED PROCUREMENT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | FAPS (EU FUNDS) | 9021469.3
SUB-TOTAL | [15 empty] | 9021469.3
OFFICE DEVICE AND EQUIPMENT | AS | NEGOTIATED PROCUREMENT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 21196530.7
| PS |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 16473.6
SUB-TOTAL | [15 empty] | 21213004.3
VEHICLE | LMD | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | FAPS (EU FUNDS) | 1350000
| AS |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | FAPS (EU FUNDS) | 29122000
| HFDB | [13 empty] | GOP | 734700000
| AS | [13 empty] | FAPS (EU FUNDS) | 1800000
SUB-TOTAL | [15 empty] | 766972000
GENERAL MERCHANDISE | HPCS | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 1563500
| DPCB-EOHO |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 14707400
SUB-TOTAL | [15 empty] | 16270900
OTHERS | HHRDB | COMPETITIVE BIDDING | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 1325500
| OSEC |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  | GOP | 300000
| BLHSD |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  |  | 850000
| DPCB-IDO |  | 3rd week November 2015 | 4th week November 2015 | 1st week December 2015 | 2nd week December 2015 | 2nd week December 2015 | 3rd week December 2015 | 3rd week December 2015 | 4th week December 2015 | 4th week December 2015 | 4th week December 2015 |  |  |  | 2000000
SUB-TOTAL | [15 empty] | 4475500
[15 empty] | TOTAL | 6533189274.17
[15 empty] | OVERALL TOTAL | 21289420161.65
SUBMITTED BY: |  |  | EVALUATED BY: |  |  |  |  | RECOMMENDING APPROVAL BY: | [6 empty] | APPROVED BY:
MA. THERESA G. VERA, MD, MHA, MSc, CESO IV |  |  | LAUREANO C. CRUZ |  |  |  |  | NEMESIO T. GAKO, MD, MPH, CESO I | [7 empty] | JANETTE LORETO GARIN, MD, MBA-H
Director IV |  |  | Officer-in-Charge, Director IV |  |  |  |  | Undersecretary of Health | [7 empty] | Secretary of Health
Procurement Service |  |  | Finance Service |  |  |  |  | Office of Administration, Finance and Procurement